## Master
User Story #2
Tasks to complete the story | Time it takes (hr)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 8 | (considering we're learning Javascript + CSS)
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 4 | 3
(B1) Build the city user tables according to the user's choice | 1 | 2
(B1) Pull data from APIs in the backend to fill out the rest of the table | 4 | 3
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 2 | 2
(B2) Build the country user tables according to the user's choice | 1 | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 2 | 2
Button 3 (B3): create a page to display, edit, and remove saved searches | 5 | 4
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 1 | 2
Set up an empty database under the user's profile so any saved searches will be stored there | 1 | 1
TOTAL | 29 | 30
Sample city user table (T1)
| User input | [6 empty] | Back-end data
| User ID* | Country of choice* | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | City1 | City2 | City3 | City4 | City5
Sample country user table (T2)
| User input | [8 empty] | Back-end data
| User ID* | Country1 * | Country2* | Country3-10 | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | Currency2* | Currency3-10

## Alex
Tasks to complete the story | Time it takes (hr)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 6
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 4
(B1) Build the city user tables according to the user's choice | 1
(B1) Pull data from APIs in the backend to fill out the rest of the table | 2
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 1
(B2) Build the country user tables according to the user's choice | 1
(B2) Pull data from APIs in the backend to fill out the rest of the table | 4
Button 3 (B3): create a page to display, edit, and remove saved searches | 3
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 2
Set up an empty database under the user's profile so any saved searches will be stored there | 3
TOTAL: | 27

## Anushka
Tasks to complete the story | Time it takes (hr)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 6
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 5
(B1) Build the city user tables according to the user's choice | 2
(B1) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 2
(B2) Build the country user tables according to the user's choice | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 3 (B3): create a page to display, edit, and remove saved searches | 5
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 2
Set up an empty database under the user's profile so any saved searches will be stored there | 2
TOTAL: | 32

## Andrew
Tasks to complete the story | ESTIMATE(hr):
Create a home page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 10 | (taking into consideration that we will have to learn/relearn CSS&HTML/Javascript and an SQL)
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 4
(B1) Build the city user tables according to the user's choice | 3
(B1) Pull data from APIs in the backend to fill out the rest of the table | 2
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 2
(B2) Build the country user tables according to the user's choice | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 1
Button 3 (B3): create a page to display, edit, and remove saved searches | 4
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 3
Set up an empty database under the user's profile so any saved searches will be stored there | 2
TOTAL: | 33

## Julia
User Story #2
Tasks to complete the story | Time it takes (hr) |  | (taking into consideration that we will have to learn/relearn CSS/Javascript and SQLAlchemy)
Create a page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 4
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 2
(B1) Build the city user tables according to the user's choice | 2
(B1) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 1
(B2) Build the country user tables according to the user's choice | 2
(B2) Pull data from APIs in the backend to fill out the rest of the table | 3
Button 3 (B3): create a page to display, edit, and remove saved searches | 4
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 1
Set up an empty database under the user's profile so any saved searches will be stored there | 1
TOTAL: | 23
Sample city user table (T1)
| User input | [6 empty] | Back-end input
| User ID* | Country of choice* | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | City1 | City2 | City3 | City4 | City5
Sample country user table (T2)
| User input | [8 empty] | Back-end input
| User ID* | Country1 * | Country2* | Country3-10 | Weather* | Inbound date* | Outbound date* | Number of passengers* | Budget* | Currency1* | Currency2* | Currency3-10

## Yansong
User Story #2
Tasks to complete the story | ESTIMATE(hr):
Create a home page with three buttons: "I know which country I want to go to", "I don't know which country I want to go to", "See my saved searches" | 10
Button 1 (B1): create a page to display and edit preferences according to Table 1 | 2
(B1) Build the city user tables according to the user's choice | 3
(B1) Pull data from APIs in the backend to fill out the rest of the table | 1
Button 2 (B2): create a page to display and edit preferences according to Table 2 | 2
(B2) Build the country user tables according to the user's choice | 3
(B2) Pull data from APIs in the backend to fill out the rest of the table | 1
Button 3 (B3): create a page to display, edit, and remove saved searches | 2
(B3) If the user clicks in one of the saved searches, it will go back to B1 or B2 accordingly | 3
Set up an empty database under the user's profile so any saved searches will be stored there | 1
TOTAL: | 28